## 📋 Project Brief
CARBON PULSE — PROJECT BRIEF
India's Carbon Market Intelligence Platform · 6-Week MVP
OVERVIEW
Product | Carbon Pulse — single-source intelligence platform for India's carbon market
Goal | Build and ship the MVP in 6 weeks with a lean 5-person team
PM | Product Designer (acting PM)
Start date | Week of 7 Jul 2026
Launch target | Week of 15 Aug 2026
SCOPE — MoSCoW
✅ Must have | All sections live with real content · Compliance checker functional · News updated weekly · Mobile responsive · Custom domain + SSL
🟡 Should have | Sticky scroll animations · Custom illustrations · Relative timestamps on news
🔵 Could have | Fully automated pipeline · CMS for content updates · Live carbon price ticker
🚫 Won't have | User accounts · Email newsletter · Multiple languages · Mobile app
SUCCESS METRICS (OKRs)
Objective | Launch a carbon market intelligence platform that people actually trust and return to
KR1 | Site live with zero broken sections or placeholder content on launch day
KR2 | News section updated within 48 hours of any major policy announcement in month 1
KR3 | Pipeline uptime above 95% in the first 30 days
KR4 | At least 3 of 5 people interviewed in week 1 say they'd bookmark the product
CIRCUIT BREAKER
⚡ If the automated pipeline is not stable by end of Week 5, it ships as manual. The launch date does not slip for it.

## 👥 Team & RACI
TEAM & RACI
TEAM
Role | Type | Time | Active Weeks | Key Responsibilities
Product Designer | Full-time | 100% | Weeks 1–6 + fractional | UX, research, IA, hi-fi design, acting PM
Full-Stack Developer | Full-time | 100% | Weeks 1–6 + on-call | Frontend build, pipeline integration, QA
Climate Content Writer | Part-time | 50% | Weeks 1–6 + 30% post | Research, all copy, weekly news review
Data Engineer | Contract | 100% | Weeks 2–5 then exit | Pipeline build, API integrations, runbook
Graphic Designer | Contract | Project | Weeks 3–4 only | Custom illustrations for How It Works
RACI — WHO OWNS WHAT
Decision / Area | Responsible | Accountable | Consulted | Informed
Scope & priorities | Product Designer | Product Designer | All team | —
Design sign-off | Product Designer | Product Designer | Developer | —
Content accuracy | Content Writer | Content Writer | Product Designer | —
Pipeline (during build) | Data Engineer | Data Engineer | Developer | Product Designer
Pipeline (post-handoff) | Developer | Developer | — | Product Designer
Launch go / no-go | Product Designer | Product Designer | All team | —
Post-launch content updates | Content Writer | Content Writer | — | Product Designer
Budget & tooling | Product Designer | Product Designer | — | All team

## ✅ Task Tracker
TASK TRACKER — Update daily. P0 = blocking today · P1 = due this week · P2 = backlog
STATUS: 🟢 Active ✅ Completed ⏳ Pending 🚫 Blocked
# | Task | Owner | Priority | Status | Due (Week) | Blocker / Notes
FOUNDATION
1 | User research — 3–5 interviews with carbon market professionals | Designer + Writer | P0 | ⏳ Pending | Week 1–2
2 | Content audit & research — fact-check all sections, fill gaps | Writer + Designer | P0 | ⏳ Pending | Week 1–2
3 | Information architecture — final page structure and order | Designer | P0 | ⏳ Pending | Week 2 | Blocked by Task 1
4 | Design system — colours, typography, components | Designer | P0 | ⏳ Pending | Week 2
BUILD
5 | Wireframes — low-fidelity layout of every section | Designer | P0 | ⏳ Pending | Week 3 | Blocked by Task 3 & 4
6 | Hi-fi design — full visual design inc. mobile layouts | Designer + Graphic | P0 | ⏳ Pending | Week 3–4
7 | Frontend build — all sections, animations, compliance checker | Developer | P0 | ⏳ Pending | Week 3–4 | Runs parallel to Task 8
8 | Content writing — all copy for every section | Content Writer | P0 | ⏳ Pending | Week 3–4 | Runs parallel to Task 7
9 | Pipeline build — RSS/API feeds, editorial review flow, runbook | Data Engineer | P1 | ⏳ Pending | Week 2–5 | Not on critical path — see circuit breaker
LAUNCH
10 | Integration — real content into build, pipeline connected | Developer + Writer | P0 | ⏳ Pending | Week 5 | Blocked by Tasks 7 & 8
11 | QA — cross-browser, mobile, content accuracy check | All team | P0 | ⏳ Pending | Week 5–6
12 | Launch — soft launch → feedback → hard launch | All team | P0 | ⏳ Pending | Week 6
POST-LAUNCH
13 | Weekly news section review and publish | Content Writer | P1 | ⏳ Pending | Ongoing
14 | Monthly policy tracker review | Content Writer | P1 | ⏳ Pending | Ongoing
15 | Pipeline monitoring and bug fixes | Developer | P1 | ⏳ Pending | Ongoing

## 📅 Gantt
GANTT — 6-WEEK BUILD PLAN
Each bar shows when that task is active. Faded bars = handoff period. Critical path: Tasks 1→3→5→7→10→12
Task | Owner | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
FOUNDATION
1. User research | Designer + Writer | █████ | █████
2. Content audit | Writer + Designer | █████ | █████
3. Information architecture | Designer |  | █████
4. Design system | Designer |  | █████
BUILD
5. Wireframes | Designer |  |  | █████
6. Hi-fi design | Designer + Graphic |  |  | █████ | █████
7. Frontend build | Developer |  |  | █████ | █████
8. Content writing | Writer |  |  | █████ | █████
9. Pipeline build | Data Eng → Dev |  | █████ | █████ | █████ | ▒▒▒
LAUNCH
10. Integration | Developer + Writer |  |  |  |  | █████
11. QA | All team |  |  |  |  | █████ | █████
12. Launch | All team | [5 empty] | █████
LEGEND: ██ Designer (green) ██ Developer (blue) ██ Content Writer (purple) ██ Data Engineer (brown) ▒▒ Handoff period

## 💰 Budget
BUDGET — CARBON PULSE MVP
All figures in INR (₹). Rates sourced from Glassdoor & PayScale India, June 2026. No equity included.
PEOPLE — BUILD PHASE (6 WEEKS)
Role | Basis | Notes | Cost (₹)
Product Designer | ₹15 LPA, 6 weeks full-time |  | 173000
Full-Stack Developer | ₹18 LPA, 6 weeks full-time |  | 208000
Climate Content Writer | ₹8 LPA, 50% time, 6 weeks |  | 46000
Data Engineer | Contract ₹1.5L/month, 4 weeks |  | 100000
Graphic Designer | Fixed project fee |  | 60000
PEOPLE SUBTOTAL |  |  | 587000
TOOLS & INFRASTRUCTURE
Item | Notes | Period | Cost (₹)
Figma | 2 seats × 2 months |  | 5000
Netlify Pro | 3 months ($20/month flat) |  | 5000
News API / RSS feed | 3 months aggregator |  | 12500
Domain (.in / .com) | 1 year |  | 1500
Contingency (10%) | Buffer for scope surprises |  | 61000
TOOLS SUBTOTAL |  |  | 85000
TOTAL MVP BUILD COST |  |  | 672000
ONGOING — MONTHLY (POST-LAUNCH)
Role / Item | Basis | Notes | Cost (₹)
Product Designer | 20% of ₹15 LPA |  | 25000
Content Writer | 30% of ₹8 LPA |  | 20000
Developer | On-call 20% |  | 30000
Hosting + tools | Netlify + API |  | 15000
MONTHLY TOTAL |  |  | 90000

## 🗣️ Standup Log
DAILY STANDUP LOG — Post by 10am in #general Slack channel. Sync call only if blockers exist.
Format: Date · Name · Yesterday · Today · Blockers · Notes
Date | Name | Yesterday | Today | Blockers | Notes
07 Jul | Designer | Kicked off user research, booked 3 interviews | Interview #1 at 11am, start IA draft | —
07 Jul | Developer | Set up repo and staging environment | Begin design system review with Designer | Waiting on Figma access | Need invite from Designer
07 Jul | Content Writer | Completed initial policy research | Content audit of existing site | —
07 Jul | Data Engineer | Pipeline architecture drafted | Begin RSS feed integration | —